## Sheet1
Process Step | Activities | Owner | Target Audience | Engagement & Communication Medium | Relevance | Tools | Timeframe
Align sponsors and Develop Vision | Clearly understand the current state & future state | Change manager | None | Live/in-Person/Video | 100% |  | Initiation phase - 2-10 days
| Conduct High-Level Change Impact Assessment (L0) | Change manager | None | Live/in-Person/Video | 100% |  | Initiation phase - 2-5 days
| Conduct change complexity & feasibility assessment | Change manager | None | N/A | 100% |  | Initiation phase - 1 day
| Develop a pre-liminary vision | Change manager | None | Live/in-Person/Video | 100% |  | Initiation phase - 1-2 days
| Identify key leaders | Change manager | None | Live/in-Person/Video | 100% |  | Initiation phase - 1-2 days
| Develop pre-liminary project briefing | Change manager | None | Live/in-Person/Video | 100% |  | Initiation phase - 1-2 days
| Meet with each key leader individually | Primary sponsor | Leaders of highly impacted functions or teams | Live/in-Person/Video | 75% |  | Initiation phase - 2-10 days
| Re-assess vision based in leader meeting | Primary sponsor | None |  | 100% |  | Initiation phase - 1 day
| Plan visioning session/off-site with leaders | Change leader | None | Live/in-Person/Video | 50% |  | Initiation phase - 1-3 days
| Host visioning session and offsite with leaders & Align on common vision for change | Primary sponsor | Impacted leaders and sponsors | Live/in-Person/Video | 50% |  | Initiation phase - 1-3 days